## CAPSTONE
Project Component | Task | Status | Completed | ETA
Data Preprocessing | Working with the 2K structured logs | Provided with Project instructions | Yes | Done
| Get Error Logs of Openstack to train the BERT |  | NO | 2023-12-01
BERT Model for anamoly detection
| Unsupervised Pre trained BERT Model for Anamoly detection | Done | Done in COLAB | Done
| Try Deep learning for Anamoly detections using logalizer | Tried to run logalizer demo.pynb. Not sure where to get the Pickle files from. How is the anamoly label attached in the data ? | NO | 1931-12-01
RCA Model | Use 3 LLM's to get the RCA analysis | 2 done - openAI and Hugging face, LLAMA is work in progress | 2 out of 3 done in COLAB | 2024-12-01
| Ensemble the 3 LLM outputs to get best outputs | Not started | NO | 2024-12-01
| Add RCA output to KB if RCA is not in KB | Not started | NO | 1931-12-01
| Use the FASTAPI instead of GRADIO to make it compatible with Chinmoys project setup | Tried it ..FAST API Still not working | NO | 1931-12-01
Colab to Production
| Combine the BERT model and RCA Model in to a single project to Github with multiple FASTAPI endpoints for demo | Work in progress | NO | 2024-01-02
| Add ClearML to each model to track versions | Work in progress | NO | 2024-01-02